## Sheet1
Group7 First Meeting
Insert your name against the time you are avaliable
| Thursday | Friday | Monday | Tuesday | Wedenesday | Thursday
start time | 2022-10-20 | 2022-10-21 | 2022-10-24 | 2022-10-25 | 2022-10-26 | 2022-10-27
10:00
11:00
12:00
13:00 |  |  |  |  | MIn,Weilu
14:00 | Zijun ,Weilu |  |  | Zijun | Min,Alice,Weilu | Zijun, Min,Alice,Weilu
15:00 | Xiangyi, Zijun, Weilu |  |  | Zijun,Alice,Weilu | Zijun, Min,Alice,Weilu | Xiangyi, Smit,Zijun, Min,Alice,Weilu, Saeed
16:00 | Xiangyi, Zijun, Weilu | Alice,Weilu |  | Zijun, Min,Alice,Weilu | Zijun, Min,Alice,Weilu | Xiangyi, Smit,Zijun, Min,Alice,Weilu, Saeed

## plan
notice: 1. we can upload every document on the file module of our group 7 on canvas. The link is https://canvas.bham.ac.uk/groups/146089. .2.there are feedback sessions from week7 to week11.
week5 | book the feedback session |  | meeting topic: discuss the pattern of the group work, like how many time we hold the meeting per week. online or offline | meeting topic: discuss the task topic | meeting topic: discuss some function of our application (the exam require at least 10 functions) so every member should give one function idea at least in order to prepare for the work of next week | meeting topic: discuss the structure of the system description essay (task A1),like how many paragraphs and what is the topic in every paragraph
week6 | book the feedback session | show the last week work | meeting topic: discuss the tool for making the coming various diagram,(open source UML packages or Visio) | meeting topic: discuss the Use Case for the next week work | A1.Describe your proposed system in 800 words (2 points) | A2. functional and non-functional requirements (2 points)
week7 | book the feedback session | show the last week work | meeting topic: discuss C1. candidate architectures styles (2 points) | learn about the tool for diagram if necessary | B1 Use Case diagram (2 points) | B2 pre/post conditions, flow of events. (2 points) | B3 scenarios/stories (2 points) | B4 Activity Diagram (1 point)
week8 | book the feedback session | show the last week work | B5. Perform Class Analysis: (2 point) | B6 Object Diagram (1 point) | B7.Sequence Diagrams (2 points) | B8 State Machine Diagrams (2 points)
week9 | book the feedback session | show the last week work | C2. Deployment Diagrams (2 Point) | C3. compare and contrast architectures (2 Points) | D.testing plan (2 points) | E1. interactive prototype (2 points)
week10 | book the feedback session | show the last week work | E2. Video recording (2 Points) | F. Ethics and Professional Practice (2 points)
week11 | book the feedback session | show the last week work | Quality, Consistency and Maturity (1 point) | Project Management and Moderation (1 point).